## Cover
Quality Management System
FAP_Test Report
FAP
Version : 1.0
Document Control information
Issue Date: | 2015-07-31
Issue Status: | Approved
Author: | ThuyLMSE02881
Reviewer information | DucHNSE02882 | PM | Required
Approver information | HaiDTSE02856 | TL
Document Revision History
Date | Version | Description | Revised by
2015-07-30 | 1 | Create document | DucHNSE02882
Note on B11: Add more reviewers as necessary
Note on B13: Add more approvers here as necessary

## Report
Test Report
Phase | # Test cases Planned | #Defects Planned | #Test cases Actual | #Defects Actual | % Tests Executed | % Tests Passed | % Tests Fail
Unit Test | 10TC/KLOC | 3 -4 | 144 | 6 | 100% | 100% | 0%
Component Test | 10TC/KLOC | 3 -4 | 145 | 0 | 100% | 100% | 0%
Integration Test | 8TC/KLOC | 2 -3 | 184 | 3 | 100% | 100% | 0%
System Test | 15TC/KLOC | 4 -6 | 341 | 5 | 100% | 100% | 0%
Total | 1400 | 240 - 340 | 669 | 14 | 100% | 100% | 0%
Phase | Round 1 |  |  |  | Round 2 |  |  |  | Round 3
| Pass | Fail | Untested | Bug | Pass | Fail | Untested | Bug | Pass | Fail | Untested | Bug
Unit Test | 144 | 0 | 0 | 0 | 144 | 0 | 0 | 0 | 144 | 0 | 0 | 0
Component Test | 145 | 0 | 0 | 0 | 145 | 0 | 0 | 0 | 145 | 0 | 0 | 0
Integration Test | 149 | 0 | 45 | 6 | 152 | 0 | 45 | 3 | 200 | 0 | 0 | 0
System Test | 166 | 21 | 155 | 35 | 266 | 21 | 55 | 35 | 377 | 0 | 0 | 0
Total | 604 | 21 | 200 | 41 | 707 | 21 | 100 | 38 | 866 | 0 | 0 | 0
Defect report
Defects | Logged | %Closed | %Invalid | %Open
Critical | 0 | 0% | 0% | 0%
High | 0 | 0% | 0% | 0%
Medium | 11 | 100% | 0% | 0%
Low | 45 | 100% | 0% | 0%
Total | 56 | 100% | 0% | 0%