## Cover
Quality Management System
DDL_Test Report
DDL
Version : 1.0
Document Control information
Issue Date: | 2015-09-12
Issue Status: | Approved
Author: | Cao Thị Phương Mai
Reviewer information | Lưu Ngọc Mạnh | PM | Required
Approver information | Vũ Công Chính | Member
Document Revision History
Date | Version | Description | Revised by
2015-09-12 | 1 | Create document | Lưu Ngọc Mạnh
Note on B11: Add more reviewers as necessary
Note on B13: Add more approvers here as necessary

## Report
Test Report
Phase | # Test cases Planned | #Defects Planned | #Test cases Actual | #Defects Actual | % Tests Executed | % Tests Passed | % Tests Fail
Unit Test | 40TC/KLOC | 3 -4 defects/KLOC |  |  | 100% | 100% | 0%
Integration Test | 30TC/KLOC | 2 -3 defects/KLOC | 300 | 1 defects/KLOC | 100% | 100% | 0%
System Test | 20TC/KLOC | 4 -6 defects/KLOC | 812 | 9 defects/KLOC | 100% | 100% | 0%
Acceptance Test | N/A | 1-2 defects/KLOC | N/A | 2 defects/KLOC | 100% | 100% | 0%
Total | 90TC/KLOC | 10-15 defects/KLOC |  | 12 defects/KLOC | 100% | 100% | 0%
Phase | Round 1 |  |  |  | Round 2 |  |  |  | Round 3
| Pass | Fail | Untested | N/A | Pass | Fail | Untested | N/A | Pass | Fail | Untested | N/A
Unit Test | 356 | 0 | 0 | 0 | 356 | 0 | 0 | 0 | 356 | 0 | 0 | 0
Integration Test | 289 | 2 | 0 | 0 | 300 | 0 | 0 | 0 | 300 | 0 | 0 | 0
System Test | 748 | 64 | 18 | 38 | 770 | 60 | 0 | 38 | 868 | 0 | 0 | 0
Total | 1393 | 66 | 18 | 38 | 1426 | 60 | 0 | 38 | 1524 | 0 | 0 | 0
Defect report
Defects | Logged | %Closed | %Invalid | %Open
Critical | 0 | 0% | 0% | 0%
High | 4 | 0% | 0% | 0%
Medium | 24 | 100% | 0% | 0%
Low | 38 | 100% | 0% | 0%
Total | 66 | 100% | 0% | 0%