## Sheet1
BẢNG THEO DÕI TIẾN ĐỘ DỰ ÁN
|  | DEVELOPER | [8 empty] | TESTER
STT | TASK (FUNTION) | PIC | Doing | Done | Total | Done Percent | Start Date | End Date | Deadline | Note | PIC | Doing | Done | Total | Percent Finish | Start Date | End Date | Deadline | Note
1 | Create Project | HuyNM | 5 | 5 | 10 | 50% | 2015-10-05 |  | 2015-10-18 |  |  | 0 | 0 | 0
2 | Edit Project | HuyNM | 5 | 5 | 10 | 50% | 2015-10-05 |  | 2015-10-18 |  |  | 0 | 0 | 0
3 | Home | TrungVN | 2 | 3 | 5 | 60% | 2015-10-05 |  | 2015-10-18 |  |  | 0 | 0 | 0
4 | Discover | TrungVN | 5 | 0 | 5 | 0% | 2015-10-05 |  | 2015-10-18 |  |  | 0 | 0 | 0
5 | Personal Page | AnhDD | 5 | 5 | 10 | 50% | 2015-10-05 |  | 2015-10-18 |  |  | 0 | 0 | 0
6 | Search | TrungVN | 5 | 0 | 5 | 0% | 2015-10-12 |  | 2015-10-18 |  |  | 0 | 0 | 0
7 | Backed Project | MaiCTP | 5 | 0 | 5 | 0% | 2015-10-12 |  | 2015-10-18 |  |  | 0 | 0 | 0
8 | Starred Project | MaiCTP | 5 | 0 | 5 | 0% | 2015-10-12 |  | 2015-10-18 |  |  | 0 | 0 | 0
9 | Created Project | MaiCTP | 5 | 0 | 5 | 0% | 2015-10-12 |  | 2015-10-18 |  |  | 0 | 0 | 0
10 | Project Details | AnhDD | 10 | 0 | 10 | 0% | 2015-10-12 |  | 2015-10-18 |  |  | 0 | 0 | 0
11 | Message | ManhLN | 5 | 5 | 10 | 50% | 2015-10-05 |  | 2015-10-18 |  |  | 0 | 0 | 0
12 | Screen Flow | ChinhVC | 5 | 0 | 5 | 0% | 2015-10-12 |  | 2015-10-18 |  |  | 0 | 0 | 0
|  |  | DEVELOP | [8 empty] | TEST
|  |  | Doing | Done | Total | [6 empty] | Doing | Done | Total
|  |  | 62 | 23 | 85 | [6 empty] | 0 | 0 | 0